Source:	HEAD acoustics GmbH

Title:	Global Analysis Lab for IVAS selection phase

Document for:	Discussion

# Introduction

For the upcoming selection phase of IVAS codec, roles (cross-check/host/listening labs) have been allocated and/or contracted so far. Only the task of Global Analysis Lab (GAL) remains, for which the source already expressed its interest in participation [1]. After internal estimates of costs and effort, HEAD acoustics GmbH would in general be able to act as the GAL in addition to the listening lab (LL) task.

# Indicative pricing

Based on preliminary clause 3.3.6 of IVAS-8a [2], the following tasks were identified for the GAL task:

- Provide random seed / shuffle of presentation orders for all listening tests (optional, if needed?),

- Coordinate and agree on exchange format of raw result data with all LLs,

- Coordinate and collect raw data from all LLs,

- Aggregate and perform statistical analyses from all experiments,

- Draft a Tdoc/report for SA4#125, which contains …

  - An overview on listening test results for each experiment,

  - Checks of performance requirements and objectives for each experiment.

- Present document at SA#125,

- Prepare changes/updates/modifications during and after meeting.

The proposal would be 12 000 € for this contracted work. The following efforts were considered in the cost calculation:

- About two weeks full-time work during and after the 6-week period of subjective testing, including a certain amount of overtime.

- Travel expenses for SA4#125

- Some overhead/budget for "smaller extra subtask(s)" (related work/questions that could possibly occur until SA4#125 or later).

# References

- S4-220152: "Interest in participation in IVAS codec selection and characterisation phase", HEAD acoustics GmbH.

- S4-230761: "IVAS Permanent Document IVAS-8a: Test Plan for Selection Phase, v.0.8.4 ", VoiceAge Corporation

Travel expenses were not taken into account by HEAD acoustics in the cost calculation for the listening lab tasks, thus there is no "double charge"!