## Slide 1: SA4 Work and Study Items Status at the start of SA4#124
Frédéric Gabin
SA4 Chair (Dolby Laboratories Inc.)
and all SA4 WID/SID Rapporteurs
(Agenda Item 5.1)

## Slide 2: Outline
Rel-18 Work Items
  Status at the end of SA4#123-e
  Rapporteur’s progress report since SA4#123-e
Rel-18 Study Items
  Status at the end of SA4#123-e
  Rapporteur’s progress report since SA4#123-e
New Work and Study items

## Slide 3: Overview of work progress Rel-18 Work Items
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
950014 | Immersive Real-time Communication for WebRTC | iRTCW | 12/2023 | 30% | SP-221032 | 50% | 
950015 | Media Capabilities for Augmented Reality | MeCAR | 12/2023 | 40% | SP-220242 | 50% | 
960042 | IMS-based AR Conversational Services | IBACS | 12/2023 -> 03/2024 | 20% | SP-230165 | 25% | 
960044 | Generic architecture for RT and AR/MR | GA4RTAR | 06/2023 | 70% | SP-220672 | 80% | Stage 2 – no other WG dependencies identified
960045 | Split Rendering Media Service Enabler | SR_MSE | 12/2023 | 25% | SP-220685 | 30% | 
960046 | Real-time Transport Protocol Configurations | 5G_RTP | 12/2023 ->03/2024 | 15% | SP-220613 | 25% | 
830005 | Terminal Audio quality performance and Test methods for Immersive Audio Services | ATIAS | 12/2023 | 30% | SP-190040 | 35% | 
770024 | EVS Codec Extension for Immersive Voice and Audio Services | IVAS_Codec | 03/2024 | 55% | SP-220608 | 60% | 
960043 | UE Testing Phase 2 | eUET | 12/2023 | 20% | SP-220610 | 22% | 
960047 | 5G Media Streaming Architecture Phase 2 | 5GMS_Ph2 | 06/2023 | 50% | SP-230164 | 65% | Stage 2 – CT3 Stage 3 work expected
980007 | Enhanced Multiparty RTT | MP_RTT | 12/2023 | 5% | SP-221346 | 15% | 
990025 | Immersive Audio for Split Rendering Scenarios | ISAR | 03/2024 | 0% | SP-230167 | 5% | 
980009 | 5G Media Streaming Audio codec phase 2 for 5G-Advanced | 5GMS_Audio_Ph2 | 03/2023 | 100% | SP-221033 | - | Complete

## Slide 4: Immersive Real-time Communication for WebRTC (iRTCW)
Rapporteur: Kyunghun Jung, Meta Ireland, kyunghun@meta.com
Progress since SA4#123-e
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  Discussed updated skeleton of TS 26.113 (S4aR230075) (telco #11, May 3)
  Discussed video format conversion (S4aR230076) (telco #11, May 3)
Any recommendations based on the agreements?
  S4aR230075 was revised to S4-230747 (with change history & minor editorials)
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Updated PD (to be assigned), TP (749 → to be assigned) can be agreed
  SWAP update (802) can be revised and agreed into TS 26.113
  Updated TS (747 → to be assigned) and cover page (748) can be agreed and sent to SA for information
  Video addition to TS (894) can be discussed and noted (to be discussed in the following telcos after revisions for, e.g., including simple descriptions of a pin-hole camera model and generic procedures for converting 2D to 3D, including rotation & translation in clause 5.3.2.1, as an example of video pre-processing, and a description of measuring sizes using the relationship of physical distance and pixel number in clause 5.3.1 Measure
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
950014 | Immersive Real-time Communication for WebRTC | iRTCW | 12/2023 | 30% | SP-221032 | 50% | 

## Slide 5: Media Capabilities for Augmented Reality (MeCAR)
Rapporteur: Emmanuel Thomas, Xiaomi, thomase@xiaomi.com
Progress since SA4#123-2
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  Further input on MPEG-I Video Decoding Interface for MeCAR (S4aV230022), clean-up needed for agreement.
  Revision submitted as S4-230811.
Any recommendations based on the agreements ?
  None.
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Examine V3C-related inputs and discuss way forward in MeCAR related to V3C technologies.
  Continue the development of the Permanent Document with QoE, Metrics and other metadata.
  Produce TS 26.119 v0.2.0 (first version with substance) based on draft specification text input.
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
950015 | Media Capabilities for Augmented Reality | MeCAR | 12/2023 | 40% | SP-220242 | 50% | 

## Slide 6: IMS-based AR Conversational Services (IBACS)
Rapporteur: Gunkel, Simon, KPN N.V., Simon.Gunkel@tno.nl
Progress since SA4#123-e
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  Contribution S4aR230078 - [IBACS] UE Rendering Call Flow- NOTED
Any recommendations based on the agreements ?
  No follow up actions from the Adhoc calls
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Continue work on PD based on input documents:
    S4-230832 3D model loading with MRF assistance
    S4-230844 Proposed updates on AR communication architecture
    S4-230845 UE centric procedures for AR communication
    S4-230879 AR rendering on UE
    S4-230909 update on Spatial description 5.1
    S4-230951 Transcoding for AR Network Rendering
  Align and trigger process to propagate TS 26.264
  Align with other related work items
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
960042 | IMS-based AR Conversational Services | IBACS | 12/2023 -> 03/2024 | 20% | SP-230165 | 25% | 
3GPP TSG SA4#124, 22-26 May 2023

## Slide 7: Generic architecture for Real-Time and AR/MR media (GA4RTAR)
Rapporteur: Hakju Ryan Lee, hakju00.lee@samsung.com
Progress since SA4#123-e
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  No agreement made: One input for update on CS3 call flow was noted
Any recommendations based on the agreements ?
  None
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Alignment of terms/APIs with 5GMS, SR-MSE, and possibly MeCAR (cross-SWG issue)
  Elaboration of call flows / procedures
  Evaluation of readiness of TS 26.506 and next way forward beyond stage-2
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
960044 | Generic architecture for RT and AR/MR | GA4RTAR | 06/2023 | 70% | SP-220672 | 80% | Stage 2 – no other WG dependencies identified

## Slide 8: Split Rendering Media Service Enabler (SR_MSE)
Rapporteur: Bouazizi, Imed, Qualcomm Incorporated, bouazizi@qti.qualcomm.com
Progress since SA4#123-e
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  A contribution to specify the signaling protocol for split rendering session setup and management was discussed.
  A contribution describing issues with referencing 5GMS and 5G-RTC architecture and procedures was discussed.
Any recommendations based on the agreements ?
  More details to the signaling protocol are expected in #124.
  A general discussion on the GA4RTAR and 5GMS architectures should take place to clarify the baseline architecture and procedures for SR_MSE.
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Agree contribution on AF, User Plane, and Client APIs and functionality.
  Discuss and agree contributions on media formats and requements.
  Align with related work items.
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
960045 | Split Rendering Media Service Enabler | SR_MSE | 12/2023 | 25% | SP-220685 | 30% | 

## Slide 9: Real Time Transport Protocol Configurations (5G_RTP)
Rapporteur: Igor Curcio, igor.curcio@nokia.com
Progress since SA4#123-e
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  1 conference call. A Contribution on “Reuse of RTP header extensions in multiple streams” was NOTED -> No agreements.
Any recommendations based on the agreements?
  None
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Continue work mainly based on proposals about the RTP header extension work on
    Fields for Data burst information
    SDP signaling
    Guidelines for marking PDU Set importance field
    PDU Set Size semantics
    Reuse of rendered pose in multiple streams
    Pose information
  Update TS 26.522
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
960046 | Real-time Transport Protocol Configurations | 5G_RTP | 12/2023 ->03/2024 | 15% | SP-220613 | 25% | 
3GPP TSG SA4#124, 22-26 May 2023

## Slide 10: Terminal Audio quality performance and Test methods for Immersive Audio Services (ATIAS)
Rapporteurs:
Stéphane Ragot, Orange, stephane.ragot@orange.com (requirements)
Stefan Bruhn, Dolby Laboratories Inc., stefan.bruhn@dolby.com (test methods)
Progress since SA4#123-e
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  N/A (No telco)
Any recommendations based on the agreements ?
  N/A
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Continue working on PD based on contributions
    S4-230882 (Xiaomi, spatial perception test)
    S4-230910 (Nokia, direction of arrival)
    S4-230911 (Nokia, lowest freq)
    S4-230917 (Dolby & al, comments to ATIAS-1)
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
830005 | Terminal Audio quality performance and Test methods for Immersive Audio Services | ATIAS | 12/2023 | 30% | SP-190040 | 35% | 

## Slide 11: EVS Codec Extension for Immersive Voice and Audio Services (IVAS_Codec)
Rapporteurs:
Su, Huan-yu, Huawei Technologies Co Ltd., hs@qosound.com
Varga, Imre, Qualcomm Incorporated, ivarga@qti.qualcomm.com
Progress since SA4#123-e
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  Continued progress on Selection Test Plan (IVAS-8a) and Selection Processing Plan (IVAS-7a), together with a fix to Design Constraints (IVAS-4)
  Discussion on floating point to fixed point conversion by a 3rd party
  Legal framework (NDA) progressed to cover test samples
Any recommendations based on the agreements ?
  Follow Project Plan (IVAS-2) which reflects now the submission date
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Continue towards finalization of Selection Test Plan (IVAS-8a) and Selection Processing Plan (IVAS-7a) (note that completion is scheduled for SA4#124)
  Selection Rules (IVAS-5) and Selection Deliverables (IVAS-6) appear completed (note that completion is scheduled for SA4#124)
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
770024 | EVS Codec Extension for Immersive Voice and Audio Services | IVAS_Codec | 03/2024 | 55% | SP-220608 | 60% | 

## Slide 12: Enhancements to UE Testing (eUET)
Rapporteurs:
Stéphane Ragot, Orange, stephane.ragot@orange.com (requirements in 26.131, new TS)
Jan Reimes, HEAD acoustics, Jan.Reimes@head-acoustics.com (test methods in 26.132)
Progress since SA4#123-e
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  N/A - No adhoc calls
Any recommendations based on the agreements ?
  N/A - No adhoc calls
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  S4-230941: Proposal for implementation of new JBM performance in TS 26.131/132
  S4-230898: Discuss possible performance requirements for Handset UE, Handheld-/Desktop Hands-free UE based on test results
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
960043 | UE Testing Phase 2 | eUET | 12/2023 | 20% | SP-220610 | 22% | 

## Slide 13: 5G Media Streaming Architecture Phase2 (5GMS_Ph2)
Rapporteur: Iraj Sodagar, Tencent, irajs@live.com
Progress since SA4#123-e
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
Any recommendations based on the agreements?
  Continue the discussion on these topics and progress the work toward completion
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  11 Contributions on the uplink, M3, feature description, dynamic policies/service operation point for low latency, multiple-manifests, data-collection, service URL, and network assistance on throughput prediction topics
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
960047 | 5G Media Streaming Architecture Phase 2 | 5GMS_Ph2 | 06/2023 | 50% | SP-230164 | 65% | Stage 2 – CT3 Stage 3 work expected
Feature description and ow latency | The endorsed CR in #123 meeting was updated with 4.0 subclauses on the general features description as the basis for further work
Data collection for ANBR-based NA | Not treated.

## Slide 14: Enhanced Multiparty RTT (MP_RTT)
Rapporteur: Huan-yu Su, su.huanyu@huawei.com
Progress since SA4#123-e
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  N/A
Any recommendations based on the agreements ?
  Continue architecture and call flow definitions
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Update general requirements
  Get the architecture and call flow for RTP solution agreed
  Update the PD for future work
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
980007 | Enhanced Multiparty RTT | MP_RTT | 12/2023 | 5% | SP-221346 | 15% | 

## Slide 15: Immersive Audio for Split Rendering Scenarios (ISAR)
Rapporteur: Stefan Bruhn, Dolby Laboratories Inc., email: stefan.bruhn@dolby.com
Progress since SA4#123-e
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  3 contributions to requirements TR received, discussed and noted
Any recommendations based on the agreements ?
  Focus on progressing draft requirements TR
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Working on draft requirements TR based on contributions S4-230842, S4-230947, S4-230944/954,
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
990025 | Immersive Audio for Split Rendering Scenarios | ISAR | 03/2024 | 0% | SP-230167 | 5% | Updates to draft TR 26.862

## Slide 16: Overview of work progress Study Items
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
870013 | Traffic Models and Quality Evaluation Methods for Media and XR Services in 5G Systems | FS_XRTraffic | 06/2023 | 90% | SP-210043 | 90% | 
950011 | Study on Artificial Intelligence (AI) and Machine Learning (ML) for Media | FS_AI4Media | 12/2023 | 25% | SP-220328 | 30% | 
960048 | Study on Media Streaming aspects of Network Slicing Phase 2 | FS_MS_NS_Ph2 | 12/2023 | 25% | SP-220675 | 30% | 
950012 | Study on immersive Real-time Communication for WebRTC Phase 2 | FS_eiRTCW | 03/2024 | 35% | SP-220239 | 40% | 
950013 | Study on Smartly Tethering AR Glasses | FS_SmarTAR | 06/2023 | 70% | SP-220240 | 77% | 
960049 | Study on AR and MR QoE Metrics | FS_ARMRQoE | 12/2023 | 15% | SP-220616 | 20% | 
980008 | Study on Diverse audio Capturing system for End-user Devices | FS_DaCED | 09/2024 | 5% | SP-221330 | 20% | Rel-19
960050 | Study on Audio Aspects for Glasses-type AR/MR Devices | FS_Audio_5GSTAR | 12/2022 | 100% | SP-220617 |  | Complete
940010 | Study on 5G Media Service Enablers | FS_5G_MSE | 12/2022 | 100% | SP-211338 |  | Complete

## Slide 17: Feasibility Study on Typical Traffic Characteristics for XR Services and other Media (FS_XRTraffic)
Rapporteur: Thomas Stockhammer, tsto@qti.qualcomm.com
Progress since SA4#123-e
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  One contribution was noted and is submitted in progressed form from this meeting
Any recommendations based on the agreements ?
  Not applicable
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Review two input contributions
  Attempt completion of the work item, and if not possible Update the work plan in order to ensure that completion of the study item can happen during SA4#125
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
870013 | Traffic Models and Quality Evaluation Methods for Media and XR Services in 5G Systems | FS_XRTraffic | 06/2023 | 90% | SP-210043 | 90% | 
 | FS_XRTraffic (Feasibility Study on Typical Traffic Characteristics for XR Services and other Media) | 
S4-230810 | [FS_XRTraffic] Proposed Updates to TR 26.926 | Qualcomm CDMA Technologies
S4-230812 | [FS_XRTraffic] Proposed Updated Time Plan | Qualcomm incorporated
S4-230821 | [FS_XRTraffic] Proposed Updates to TR 26.925 | Qualcomm Tech. Netherlands B.V

## Slide 18: Feasibility Study on Artificial Intelligence (AI) and Machine Learning (ML) for Media (FS_AI4Media)
Rapporteur: Eric Yip, eric.yip@samsung.com
Progress since SA4#123-e
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  Two contributions were discussed during the post #123 adhoc call, one on testbed architectures for evaluation framework (noted and to be revised @ #124), one on a model compression for NLP scenario which was agreed.
Any recommendations based on the agreements ?
  There was an initial discussion regarding a repository for the scripts and datasets required for the evaluation.
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  13 contributions in total, 7 related to evaluation framework.
  Plan for #124:
    Introduce stable text on architectures and flows to TR
    Discuss way forward regarding evaluation repository for scripts and datasets
    Discuss tentative time/workplan for evaluation of scenarios
    Consider separate PD and TR for documentation of evaluation (including possible update of WID)
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
950011 | Study on Artificial Intelligence (AI) and Machine Learning (ML) for Media | FS_AI4Media | 12/2023 | 25% | SP-220328 | 30% | 

## Slide 19: Study on Media Streaming aspects of Network Slicing Phase 2 (FS_MS_NS_Ph2)
Rapporteur: Prakash Kolan, p.kolan@samsung.com
Progress since SA4#123-e
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  None
Any recommendations based on the agreements ?
  None
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Study on candidate solutions for agreed key #3 (network slice replacement)
  Continue study on new key issues in scope of TR 26.941
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
960048 | Study on Media Streaming aspects of Network Slicing Phase 2 | FS_MS_NS_Ph2 | 12/2023 | 25% | SP-220675 | 30% | 

## Slide 20: Feasibility Study on the enhancements for immersive Real-time Communication for WebRTC (FS_eiRTCW)
Rapporteur: INOUE, Yoshihiro, NTT(TTC), Yoshihiro Inoue yoshihiro.inoue@ntt-at.co.jp
Progress since SA4#123-e
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  None
Any recommendations based on the agreements ?
  None
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Discuss the following submitted contributions and update the Permanent Document.
    High-level network model and target use cases (S4-230850)
    Possible architecture for collaboration scenario#4 (S4-230851)
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
950012 | Study on immersive Real-time Communication for WebRTC Phase 2 | FS_eiRTCW | 03/2024 | 35% | SP-220239 | 40% | 

## Slide 21: Feasibility Study on Smartly Tethering AR Glasses (FS_SmarTAR)
Rapporteur: Thomas Stockhammer, Qualcomm Incorporated, tsto@qti.qualcomm.com
Progress since SA4#123-e
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  One contribution was agreed during the AHG and implemented in the Editor's Updates: S4aI230094 - RTP header extension for in-band delay measurement
Any recommendations based on the agreements ?
  It is recommended to adopt the agreements by agreeing the following input document to SA4#123
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Review input contributions that progress the key issues
  Prepare TR26.806 to be sent for approval and complete study item
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
950013 | Study on Smartly Tethering AR Glasses | FS_SmarTAR | 06/2023 | 70% | SP-220240 | 77% | 
 | FS_SmarTAR (Feasibility Study on Smartly Tethering AR Glasses) | 
S4-230813 | [FS_SmarTAR] Key Issue #5: Compute distribution across UE and network for tethered glasses | Qualcomm incorporated
S4-230819 | [FS_SmarTAR] Editor's Proposed Updates | Qualcomm Tech. Netherlands B.V
S4-230820 | [FS_SmarTAR] Proposed Finalization of TR | Qualcomm Tech. Netherlands B.V
S4-230847 | [FS_SmarTAR] Methods for achieving desired end-to-end packet error rate and bit rate | Qualcomm Technologies Ireland
S4-230853 | General corrections and editorial modifications | Nokia
S4-230854 | Call flows for standalone AR glasses-based device architecture | Nokia

## Slide 22: Feasibility Study on AR and MR QoE Metrics (FS_ARMRQoE)
Rapporteur: Shuai Gao (gaos30@chinaunicom.cn)
Progress since SA4#123-e
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  No progress.
Any recommendations based on the agreements ?
  No progress.
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Discussion on the parameters that can be monitored via the Observation Point 1.
  Discussion on relevant AR/MR QoE metrics, e.g. pose predication error, one-way delay, and device-related QoE metrics.
  Capture the agreements and update the TR 26.812.
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
960049 | Study on AR and MR QoE Metrics | FS_ARMRQoE | 12/2023 | 15% | SP-220616 | 20% | 

## Slide 23: Study on Diverse audio Capturing system for End-user Devices (FS_DaCED)
Rapporteur: Wang Bin, Xiaomi, email: wangbin23@xiaomi.com
Progress since SA4#123-e
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  No progress
Any recommendations based on the agreements ?
  n/a
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  n/a
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
980008 | Study on Diverse audio Capturing system for End-user Devices | FS_DaCED | 09/2024 | 5% | SP-221330 | 20% | Rel-19

## Slide 24: New Work Item(s)
Note: Progress since last SA is shown with blue colour.
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment