## Slide 1: SA4 Work and Study Items Status at the start of SA4#126
Frédéric Gabin
SA4 Chair (Dolby Laboratories Inc.)
and all SA4 WID/SID Rapporteurs
(Agenda Item 5.1)

## Slide 2: Outline
Rel-18 Work Items
  Status at the end of SA4#125/SA#101
  Rapporteur’s progress report since SA4#125
Rel-18 Study Items
  Status at the end of SA4#125/SA#101
  Rapporteur’s progress report since SA4#125

## Slide 3: Overview of work progress Rel-18 Work Items – after SA#101 (1/2)
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
950014 | Immersive Real-time Communication for WebRTC | iRTCW | 3/3/2024 | 50% | SP-230977 |  | 
950015 | Media Capabilities for Augmented Reality | MeCAR | 3/3/2024 | 65% | SP-220242 |  | 
960042 | IMS-based AR Conversational Services | IBACS | 3/3/2024 | 35% | SP-230165 |  | 
960044 | Generic architecture for RT and AR/MR | GA4RTAR | 6/6/2023 | 100% | SP-220672 |  | Stage 2 – Complete
960045 | Split Rendering Media Service Enabler | SR_MSE | 3/3/2024 | 50% | SP-220685 |  | 
960046 | Real-time Transport Protocol Configurations | 5G_RTP | 3/3/2024 | 45% | SP-230541 |  | 
830005 | Terminal Audio quality performance and Test methods for Immersive Audio Services | ATIAS | 3/3/2024 | 50% | SP-190040 |  | 
770024 | EVS Codec Extension for Immersive Voice and Audio Services | IVAS_Codec | 3/3/2024 | 75% | SP-220608 |  | 
960043 | UE Testing Phase 2 | eUET | 3/3/2024 | 35% | SP-220610 |  | 
980009 | 5G Media Streaming Audio codec phase 2 for 5G-Advanced | 5GMS_Audio_Ph2 | 3/3/2023 |  | SP-221033 |  | Complete
960047 | 5G Media Streaming Architecture Phase 2 | 5GMS_Ph2 | 6/6/2023 | 100% | SP-230164 |  | Stage 2 – Complete
980007 | Enhanced Multiparty RTT | MP_RTT | 12/12/2023 | 50% | SP-221346 |  | 

## Slide 4: Overview of work progress Rel-18 Work Items – after SA#101 (2/2)
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
990025 | Immersive Audio for Split Rendering Scenarios | ISAR | 3/3/2024 | 15% | SP-230167 |  | 
1000015 | 5G-Advanced media profiles for messaging services | PROMISE | 3/3/2024 | 15% | SP-230542 |  | 
1000018 | 5G Media Streaming Protocols Phase 2 | 5GMS_Pro_Ph2 | 3/3/2024 | 25% | SP-230976 |  | 

## Slide 5: Immersive Real-time Communication for WebRTC (iRTCW)
Rapporteur: Dr. Hakju Ryan Lee (Samsung) hakju00.lee@samsung.com
Progress since SA4#125
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  Agreed to create a new TS for RTC media capabilities and profiles (26.xyz)
  Skeleton of draft 26.xyz agreed as baseline (S4aR230120)
  RTC-specific APIs with association to 5GMS discussed
Any recommendations based on the agreements?
  To revise WID to add a new specification (26.xyz)
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Confirm the list of RTC APIs : Configuration, Metric reporting, Dynamic policies, etc
  Update TS 26.510 (under 5GMS_Pro_Ph2) and TS 26.113 accordingly
  Agree on TS 26.113 v1.0.0 to be presented to SA plenary for information
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
950014 | Immersive Real-time Communication for WebRTC | iRTCW | 3/3/2024 | 50% | SP-230977 |  | 

## Slide 6: Media Capabilities for Augmented Reality (MeCAR)
Rapporteur: Emmanuel Thomas, Xiaomi, thomase@xiaomi.com
Progress since SA4#125
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  One input received on latency metrics and revised to S4-231795.
  No agreement made.
Any recommendations based on the agreements?
  None
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Produce TS 26.119 v1.0 by handling in priority input contributions on:
    media capabilities definitions (audio, video and scene)
    device categories definitions and capabilities support
  Update the Permanent Document as needed based on other input contributions.
  Review S4-231859 “MeCAR status overview” to discuss next steps related to other MeCAR’s output.
  Coordinate with IBACS (1874), iRTCW (1839) and SR_MSE (1872) delegates on depth support in MeCAR (1860).
  Coordinate with SR_MSE (1883) delegates on metadata definition (pose and action) in MeCAR (1861).
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
950015 | Media Capabilities for Augmented Reality | MeCAR | 3/3/2024 | 65% | SP-220242 |  | 

## Slide 7: IMS-based AR Conversational Services (IBACS)
Rapporteur: Gunkel, Simon, KPN N.V., Simon.Gunkel@tno.nl
Progress since SA4#124
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  S4aR230099 & S4aR230121 agreed into TS -> 26264-021 (S4-231783)
Any recommendations based on the agreements ?
  No follow up actions from the Adhoc calls
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Continue work on PD based on input documents:
    S4-231728 transcoding & network rendering (incl. call flows); S4-231744 rendering call flow
  Continue work on TS 26.264
    S4-231627 AR Call Flow / Data Transport; S4-231784 AR-MTSI clients; S4-231785 network media rendering; S4-231793 AR IMS DC architecture; S4-231873 MIV / MeCAR; S4-231874 Texture and depth
  Discuss clear way to completion
3GPP TSG SA4#126, 14-18 November 2023
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
960042 | IMS-based AR Conversational Services | IBACS | 3/3/2024 | 35% | SP-230165 |  | 

## Slide 8: Split Rendering Media Service Enabler (SR_MSE)
Rapporteur: Bouazizi, Imed, Qualcomm Incorporated, bouazizi@qti.qualcomm.com
Progress since SA4#125
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  …
Any recommendations based on the agreements?
  …
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  …
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
960045 | Split Rendering Media Service Enabler | SR_MSE | 3/3/2024 | 50% | SP-220685 |  | 

## Slide 9: Real Time Transport Protocol Configurations (5G_RTP)
Rapporteur: Igor Curcio, igor.curcio@nokia.com
Progress since SA4#125
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  Agreed clarifications for PDU Set guidelines (about PSI)
Any recommendations based on the agreements?
  Finalize the RTP HE for rendered pose which was first agreed and then noted.
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Discuss 16 input contributions
    13 on PDU Sets
    1 on RTP HE for e2e delay measurement
    1 on RTCP XR feedback for QoE reporting
    1 TS
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
960046 | Real-time Transport Protocol Configurations | 5G_RTP | 3/3/2024 | 45% | SP-230541 |  | 
3GPP TSG SA4#124, 22-26 May 2023

## Slide 10: Terminal Audio quality performance and Test methods for Immersive Audio Services (ATIAS)
Rapporteurs:
Stéphane Ragot, Orange, stephane.ragot@orange.com (requirements)
Stefan Bruhn, Dolby Laboratories Inc., stefan.bruhn@dolby.com (test methods)
Progress since SA4#125
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  Receive tests for SBA and MASA were agreed to be included in the ATIAS Pdoc
Any recommendations based on the agreements?
  Editor’s updates of ATIAS Pdoc on inclusion the agreed receive tests to be reviewed
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Review 3 inputs on receive loudness tests and agree on common ground
  Review and agree suggested updates of test for stereo UE in ATIAS Pdoc
  Review and agree proposed UE classification and test structure for ATIAS
  Discuss comments on ATIAS regarding codec operation and structure of requirements, extension of 3GPP TS 26.260, and receiver tests
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
830005 | Terminal Audio quality performance and Test methods for Immersive Audio Services | ATIAS | 3/3/2024 | 50% | SP-190040 |  | 

## Slide 11: EVS Codec Extension for Immersive Voice and Audio Services (IVAS_Codec)
Rapporteurs:
Su, Huan-yu, Huawei Technologies Co Ltd., hs@qosound.com
Varga, Imre, Qualcomm Incorporated, ivarga@qti.qualcomm.com
Progress since SA4#125
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  Progress made on characterization phase activities planning.
Any recommendations based on the agreements?
  Characterization phase test plan and processing plan will be developed and submitted to SA4#126 for consideration.
  Work on floating point code to fixed-point code conversion has started, keep activity on track, secure schedule, and successful technical content.
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Further update the characterization phase planning, e.g., test conditions, test methodologies to cover operating conditions not tested in the selection phase, 3rd party testing vs IVAS PC proponent shared testing, etc.
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
770024 | EVS Codec Extension for Immersive Voice and Audio Services | IVAS_Codec | 3/3/2024 | 75% | SP-220608 |  | 

## Slide 12: Enhancements to UE Testing (eUET)
Rapporteurs:
Stéphane Ragot, Orange, stephane.ragot@orange.com (requirements in 26.131, new TS)
Jan Reimes, HEAD acoustics, Jan.Reimes@head-acoustics.com (test methods in 26.132)
Progress since SA4#125
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  No inputs received.
Any recommendations based on the agreements?
  n/a
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  S4-231617: CR on TR 26.801 with round robin test results of HaNTE work item, which was submitted for agreement and approval.
  S4-231778: CR on TS 26.131 on SWB performance requirements for desktop hands-free UE, headset UE, and handheld hands-free UE. Start of formal work, provisional values will be discussed during the meeting. CR will most likely be revised and used as basis for further work.
  S4-231832: Updated proposal for delay & loss profile and an initial proposal for a CR on TS 26.131/132 in an Annex (start of formal work). The Annex will most likely also be revised into a CR used as basis for further work.
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
960043 | UE Testing Phase 2 | eUET | 3/3/2024 | 35% | SP-220610 |  | 

## Slide 13: Enhanced Multiparty RTT (MP_RTT)
Rapporteur: Huan-yu Su, su.huanyu@huawei.com
Progress since SA4#125
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  A draft CR to TS 26.114 was presented and discussed, comments were received
Any recommendations based on the agreements?
  A revised CR was worked out off-line and is submitted to SA4#126 for consideration
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  If the CR or its further revision is agreed and approved by SA4, then the WI is completed
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
980007 | Enhanced Multiparty RTT | MP_RTT | 12/12/2023 | 50% | SP-221346 |  | 

## Slide 14: Immersive Audio for Split Rendering Scenarios (ISAR)
Rapporteur: Stefan Bruhn, Dolby Laboratories Inc., email: stefan.bruhn@dolby.com
Progress since SA4#125
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  Sections on General Design Guidelines, Physical and Functional Design Constraints significantly progressed with main parts agreed.
Any recommendations based on the agreements?
  As the General Design Guidelines give guidance on objectives of Immersive Audio Split Rendering,, next should be to focus on performance requirements.
  If progress can be made on the section on connectivity scenarios (editorial improvements/completions) and performance requirements, the TR is sufficiently complete for presentation to SA (for information)
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Review editor’s edits after Adhoc calls, especially the section on connectivity scenarios
  Discuss and agree inputs on performance requirements
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
990025 | Immersive Audio for Split Rendering Scenarios | ISAR | 3/3/2024 | 15% | SP-230167 |  | 

## Slide 15: 5G-Advanced media profiles for messaging services (PROMISE)
Rapporteur: Frédéric Gabin, Dolby Laboratories Inc., email: frederic.gabin@dolby.com
Progress since SA4#125
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  No discussions during MBS AH Telcos
  ISO/IEC JTC 1/SC29 agreed a new work item on “MeMAF” as response to SA4 LS.
  GSMA NG/UPG reviewed the incoming SA4 LS on PROMISE and forwarded it to GSMA NG/GSG which is working on RCS aspects.
Any recommendations based on the agreements?
  Update work plan
  Focus first on TS 26.140 and 26.143
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Incoming LS from ISO/IEC JTC 1/SC29 to be handled at SA4#126: Consider MeMAF as potential file format for TS 26.143.
  Discuss 3D scenes and assets format
  Discuss upgrades to video profiles
  Progress review of existing TS 26.140 and TS 26.141 formats for potential removal
  Progress and endorse CR to TS 26.140
  Agree draft TS 26.143 Messaging Media profiles v0.4.0 as basis for further work
  Update Work Plan
  Send LS to GSMA NG/UPG and GSMA NG/GSG and ISO/IEC JTC 1/SC29 as update on 5G-Advanced formats and codecs for messaging services
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1000015 | 5G-Advanced media profiles for messaging services | PROMISE | 3/3/2024 | 15% | SP-230542 |  | 

## Slide 16: 5G Media Streaming Protocols Phase 2 (5GMS_Pro_Ph2)
Rapporteur: Thomas Stockhammer, Qualcomm Incorporated, tsto@qti.qualcomm.com, General & topics 2, 3, 4, 5, 7, 8, 9, 10, 13
Iraj Sodagar, Tencent, irajs@live.com, for topics 1, 6, 11, 12
Progress since SA4#125
Revised WID approved at SA#101
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  A document was endorsed for API changes to support 3GPP Service URL S4aI230150
  A discussion paper was agreed in order to Refactor the Service Access Information API in S4aI230152
  Discussion on media refererence architecture to with new references and APIs progressed in S4aI230168 – also ported to permanent document
  An updated Open API design was agreed in S4aI230154
  Additional discussion on BDT and other functionalities in the context of stage 2
Any recommendations based on the agreements?
  Carry forward the above agreements by agreeing S4-231637, S4-231641, S4-231642 early in the process
  Address any open stage-2 issues that impact stage-3 decisions early: S4-231628, S4-231629, S4-231630, S4-231640, S4-231643, S4-231658, S4-231677
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  We have significant input to all 13 work item objectives
  Expect that first set of CRs may be completed, but possibly not yet sent to SA plenary to deal with TS 26.510 and TS 26.512 structuring
  Send TS 26.510 to SA plenary for information
  Schedule sufficient online time, also with colleagues from RTC to progress the work and also address scheduling of work after SA4#126 in AHGs
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1000018 | 5G Media Streaming Protocols Phase 2 | 5GMS_Pro_Ph2 | 3/3/2024 | 25% | SP-230976 |  | 

## Slide 17: Overview of work progress Study Items – after SA#101
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
870013 | Traffic Models and Quality Evaluation Methods for Media and XR Services in 5G Systems | FS_XRTraffic | 9/9/2023 | 100% | SP-210043 |  | Complete
950011 | Study on Artificial Intelligence (AI) and Machine Learning (ML) for Media | FS_AI4Media | 3/3/2024 | 40% | SP-220328 |  | 
960048 | Study on Media Streaming aspects of Network Slicing Phase 2 | FS_MS_NS_Ph2 | 12/12/2023 | 65% | SP-220675 |  | 
950012 | Study on immersive Real-time Communication for WebRTC Phase 2 | FS_eiRTCW | 3/3/2024 | 55% | SP-220239 |  | 
950013 | Study on Smartly Tethering AR Glasses | FS_SmarTAR | 6/6/2023 | 100% | SP-220240 |  | Complete
960049 | Study on AR and MR QoE Metrics | FS_ARMRQoE | 3/3/2024 | 50% | SP-220616 |  | 
980008 | Study on Diverse audio Capturing system for End-user Devices | FS_DaCED | 9/9/2024 | 35% | SP-221330 |  | Rel-19
960050 | Study on Audio Aspects for Glasses-type AR/MR Devices | FS_Audio_5GSTAR | 12/12/2022 | 100% | SP-220617 |  | Complete
940010 | Study on 5G Media Service Enablers | FS_5G_MSE | 12/12/2022 | 100% | SP-211338 |  | Complete
1000016 | Feasibility Study on Film Grain synthesis | FS_FGS | 12/12/2023 | 10% | SP-230539 |  | 
1000017 | Feasibility Study on new HEVC profiles and operating points | FS_HEVC_Profiles | 3/3/2024 | 30% | SP-230540 |  | 
1000019 | Feasibility Study on Avatars for Real-Time Communication | FS_AVATAR | 3/3/2024 | 5% | SP-230544 |  | 

## Slide 18: Feasibility Study on Artificial Intelligence (AI) and Machine Learning (ML) for Media (FS_AI4Media)
Rapporteur: Eric Yip, eric.yip@samsung.com
Progress since SA4#125
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  [S4aV230063 Description for bit-incremental transmission scenario] was agreed to the evaluation PD
  Details on the way forward for the evaluations & study item were also discussed (see details in S4-231773)
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Make progress on text for dTR 26.927 (6 pCRs)
  Review & discuss feasibility evaluation progress on split inference scenarios (scripts from 3 different companies)
  Make progress on other aspects related to contents in PD
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
950011 | Study on Artificial Intelligence (AI) and Machine Learning (ML) for Media | FS_AI4Media | 3/3/2024 | 40% | SP-220328 |  | 

## Slide 19: Study on Media Streaming aspects of Network Slicing Phase 2 (FS_MS_NS_Ph2)
Rapporteur: Prakash Kolan, p.kolan@samsung.com
Progress since SA4#125
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  No contributions were discussed during Adhoc calls
Any recommendations based on the agreements?
  No agreements
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Review LS reply from SA2 on network slice replacement
  Review contributions on two key issues and candidate solutions and way forward on network slice replacement
  Review contributions on conclusions and recommendations for the study, and adoption of TR 26941 agreements into stage-3 specification
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
960048 | Study on Media Streaming aspects of Network Slicing Phase 2 | FS_MS_NS_Ph2 | 12/12/2023 | 65% | SP-220675 |  | 

## Slide 20: Feasibility Study on the enhancements for immersive Real-time Communication for WebRTC (FS_eiRTCW)
Rapporteur: INOUE, Yoshihiro, NTT(TTC), Yoshihiro Inoue yoshihiro.inoue@ntt-at.co.jp
Progress since SA4#125
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  7 contributions were discussed.
    New key issue and the solution (WSF discovery mechanism) in S4aR230097 was agreed to incorporate into eIRTCW PD.
    Key Issue #4 (Interworking with IMS) in S4aR230112 and new key issue (Protocol-level interworking between RTC network and IMS) in S4aR230114 were agreed to incorporate into eIRTCW PD. The corresponding solutions in S4aR230113 and S4aR230115 were just noted.
    New key issue (Requirements for service control API) in S4aR230116 and skeleton of TR 26.930 in S4aR230117 were postponed till Chicago meeting.
Any recommendations based on the agreements ?
  Regarding the IMS related key issues and solutions (i.e., KI#4/Sol#4/new KI/new Sol), the LS to ask the feedback about the impact on IMS specifications should be send to SA2 before incorporating the description of PD into TR 26.930. (S4aR230112/S4aR230113/S4aR230114/S4aR230115)
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Discuss the submitted contributions and update the Permanent Document.
    KI#8/Sol#8 (Details of signalling protocol) in S4-231721, Sol#4 (Interworking with IMS) in S4-231722, new Sol (Protocol-level interworking between RTC network and IMS) in S4-231723, new KI (Requirements for service control API) in S4-231725, KI#5 (Tethering Cases) in S4-231812, KI#6 (Security Considerations) in S4-231724 and message examples in S4-231726.
  Discuss the submitted contributions.
    TR 26.930 Skeleton (S4-231727)
    pCRs for TR 26.930: Scope (S4-231729), Reference (S4-231750), difinitions/symbols/abbreviations (S4-231749), motivation (S4-231730), Architecture (KI and Sol) (S4-231731, S4-231738), requirements for C-Plane signalling (KI and Sol) (S4-231732, S4-231739), details of signalling protocol (KI) (S4-231733), requirements for U-Plane (KI and Sol) (S4-231734, S4-231740), requirements for service control API (KI) (S4-231735), WSF discovery mechanism (KI and Sol) (S4-231736, S4-231741) and security considerations (KI) (S4-231737).
    LS out to ask the feedback about the impact on IMS specifications. (to SA2) (S4-231719)
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
950012 | Study on immersive Real-time Communication for WebRTC Phase 2 | FS_eiRTCW | 3/3/2024 | 55% | SP-220239 |  | 

## Slide 21: Feasibility Study on AR and MR QoE Metrics (FS_ARMRQoE)
Rapporteur: Shuai Gao (gaos30@chinaunicom.cn)
Progress since SA4#125
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  No progress.
Any recommendations based on the agreements?
  No progress.
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Align the definition of observation points to MeCar TS 26.119, and address the Editor’s note in the TR 26.812.
  Add explanations to address the editor’s notes in the Anchor Untracked Ratio QoE.
  Discuss whether to define Pose correction or reprojection error metrics.
  Capture the agreements and update the TR 26.812, and send it to SA plenary for information if the complete level is greater than or equal to 60%.
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
960049 | Study on AR and MR QoE Metrics | FS_ARMRQoE | 3/3/2024 | 50% | SP-220616 | 50 | 

## Slide 22: Study on Diverse audio Capturing system for End-user Devices (FS_DaCED)
Rapporteur: Wang Bin, Xiaomi, email: wangbin23@xiaomi.com
Progress since SA4#125
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  We had two #SA4-125-post meeting. Talked about sizes of earbuds, Tablets, Laptops, Watches, Glasses, and Cars. One usage Scenario for Example Capturing Processing.
  Have integrated the agreed contents into the TR26.933.
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  There are 4 contributions for this meeting.
  We are going to discuss the echo control on UE, Parametric spatial audio capture related issues, and one correction to progress the project
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
980008 | Study on Diverse audio Capturing system for End-user Devices | FS_DaCED | 9/9/2024 | 35% | SP-221330 |  | Rel-19

## Slide 23: Feasibility Study on Film Grain synthesis (FS_FGS)
Rapporteur: Brian Lee (Dolby Laboratories) - Brian.Lee@dolby.com
Progress since SA4#125
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  Make partial progress in testing FGS benefits using subjective and objective test methodologies.
Any recommendations based on the agreements?
  General consensus to add more time to do more comprehensive study and collect feedback.
  Rapporteur continuing to work on additional FGS tests.
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  At SA4 #126, rapporteur plans to propose revising the time plan to complete this study by March 2024 for SA Plenary approval.
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1000016 | Feasibility Study on Film Grain synthesis | FS_FGS | 12/12/2023 | 10% | SP-230539 | 20% | Propose to complete by 3/03/2024

## Slide 24: Feasibility Study on new HEVC profiles and operating points (FS_HEVC_Profiles)
Rapporteur: Waqar Zia (waqar_zia (at) apple.com)
Progress since SA4#125
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  Updates from corresponding activities in MPEG (CMAF) were added, some updates to scope and introduction
Any recommendations based on the agreements?
  Continue working on completing the assessment of available scenarios and start drawing conclusions
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Converge on available methodology, and on new scenarios
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1000017 | Feasibility Study on new HEVC profiles and operating points | FS_HEVC_Profiles | 3/3/2024 | 30% | SP-230540 |  | 

## Slide 25: Feasibility Study on Avatars for Real-Time Communication (FS_AVATAR)
Rapporteur: Bouazizi, Imed, Qualcomm Incorporated, bouazizi AT qti DOT qualcomm DOT com
Progress since SA4#125
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  …
Any recommendations based on the agreements?
  …
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  …
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1000019 | Feasibility Study on Avatars for Real-Time Communication | FS_AVATAR | 3/3/2024 | 5% | SP-230544 |  |