## Slide 1: SA4 Work and Study Items Status at the start of SA4#129-e
Frédéric Gabin
SA4 Chair (Dolby France SAS)
and all SA4 WID/SID Rapporteurs
(Agenda Item 5.1)

## Slide 2: Outline
Rel-19 Work Items
  Status at the end of SA#104 (and SA4#128)
  Rapporteur’s progress report since SA4#128
Study Items
  Status at the end of SA#104 (and SA4#128)
  Rapporteur’s progress report since SA4#128

## Slide 3: Overview of work progress Rel-19 Work Items – after SA#104 (SA4#128)
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1030002 | Video Operating Points - Harmonization and Stereo MV-HEVC | VOPS | 3/3/2025 | - | SP-240060 | 15% | 
1030003 | Split Rendering over IMS | SR_IMS | 3/3/2025 | - | SP-240492 | 10% | 
1040021 | EVS Codec Extension for Immersive Voice and Audio Services, Phase 2 | IVAS_Codec_Ph2 | 6/6/2025 | - | SP-241000 | 0% | 

## Slide 4: Video Operating Points - Harmonization and Stereo MV-HEVC (VOPS)
Rapporteur: Waqar Zia (waqar_zia (at) apple.com)
Progress since SA4#128
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  No work to be reported from SWG calls. Based on the LS exchange with MPEG systems, some aspects of the work on CMAF and codec signaling are progressing at MPEG instead.
Any recommendations based on the agreements ?
  None
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Check details/feedback from MPEG reply LS. Progress on updates of video operating points of TS 26.265, CMAF, file format and codec strings issues from the input contributions.
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1030002 | Video Operating Points - Harmonization and Stereo MV-HEVC | VOPS | 3/3/2025 | - | SP-240060 | 15% | 

## Slide 5: Split Rendering over IMS (SR_IMS)
Rapporteur: He, Shane, Nokia Corporation, shane.he@nokia.com
Progress since SA4#128
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  One contribution related to Network Centric Procedures  noted with follow-up contribution at #129
Any recommendations based on the agreements ?
  No
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Discuss the submitted contributions and incorporate these into TS 26.567 : S4-241514 , S4-241532 , S4-241564 , S4-241615 , S4-241550
  Progress the work on general procedures of split rendering over the IMS architecture and metadata formats
  Progress the work according to the time plan
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1030003 | Split Rendering over IMS | SR_IMS | 3/3/2025 | - | SP-240492 | 15% | 

## Slide 6: EVS Codec Extension for Immersive Voice and Audio Services, Phase 2 (IVAS_Codec_Ph2)
Rapporteur: Su, Huan-yu, Huawei Technologies Co Ltd., su.huanyu@huawei.com
Progress since SA4#128
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  Agreement on allocating the unused funding for IVAS_Codec to IVAS_Codec_Ph2
  Agreement on requirements and milestones for the IVAS floating-point to fixed-point conversion
Any recommendations based on the agreements ?
  Proceed with IVAS_Codec_Ph2 tasks as stipulated in the approved WID
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Agree to a set of updates/corrections to the IVAS series of TS/TR
  Discuss and agree to the Timeplan for IVAS_Codec_Ph2
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1040021 | EVS Codec Extension for Immersive Voice and Audio Services, Phase 2 | IVAS_Codec_Ph2 | 6/6/2025 | - | SP-241000 | 0% | 

## Slide 7: Overview of work progress Study Items – after SA#104 (SA4#128)
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
950011 | Study on Artificial Intelligence (AI) and Machine Learning (ML) for Media | FS_AI4Media | 9/9/2024 -> 3/3/2025 | 60% | SP-220328 | 75% | 
980008 | Study on Diverse audio Capturing system for End-user Devices | FS_DaCED | 9/9/2024 | 70% | SP-221330 | 85% | 
1000016 | Feasibility Study on Film Grain synthesis | FS_FGS | 3/3/2025 | 30% | SP-230539 | 30% | 
1000019 | Feasibility Study on Avatars for Real-Time Communication | FS_AVATAR | 12/12/2024 | 30% | SP-230544 | 50% | 
1030004 | Study on Media enerGy consumption exposuRE and EvaluatioN framework | FS_MediaEnergyGREEN | 3/3/2025 | - | SP-240481 | 15% | 
1030005 | Study on Media Messaging | FS_MeMe | 12/12/2024 -> 3/3/2025 | - | SP-240477 | 10% | 
1030006 | Study on Advanced Media Delivery | FS_AMD | 12/12/2024 | - | SP-241011 | 15% | Revised SID
1030007 | Study of 5G Real-time Transport Protocol Configurations, Phase 2 | FS_5G_RTP_Ph2 | 12/12/2024 | - | SP-240482 | 40% | 
1030008 | Study on Beyond 2D Video | FS_Beyond2D | 3/3/2025 | - | SP-240479 | 10% | 
1030009 | Study on Audio Codec APIs | FS_ACAPI | 3/3/2025 |  | SP-240480 | 10% | 
1030002 | Study on Haptics in 5G Media Services | FS_HapticsMed | 3/3/2025 | - | SP-240979 | 0% | 
1040022 | Study on Spatial Computing for AR Services | FS_ARSpatial | 6/6/2025 | - | SP-240927 | 0% | 

## Slide 8: Feasibility Study on Artificial Intelligence (AI) and Machine Learning (ML) for Media (FS_AI4Media)
Rapporteur: Eric Yip, eric.yip@samsung.com
Progress since SA4#128
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  We had an offline after SA4#128, agreeing to work on collaboration scenarios and to start discussing conclusions, whilst continuing with evaluations
  Agreed contributions related to 3 collaboration scenarios, further details on split evaluation scenario, cross-check of model compression scenario
Any recommendations based on the agreements ?
  Continue work on agreed collaboration scenarios (architecture and gaps)
  Continue evaluation progress
  Refining dTR 26.927 contents
  Start discussing conclusions
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Same as the above
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
950011 | Study on Artificial Intelligence (AI) and Machine Learning (ML) for Media | FS_AI4Media | 9/9/2024 -> 3/3/2025 | 60% | SP-220328 | 75% | 

## Slide 9: Study on Diverse audio Capturing system for End-user Devices (FS_DaCED)
Rapporteur: Wang Bin, Xiaomi, email: wangbin23@xiaomi.com
Progress since SA4#128
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  S4aA240040, S4aA240041, S4aA240042, S4aA240043, S4aA240044, S4aA240045 were discussed and some contents were agreed to integrated into the draft TR
Any recommendations based on the agreements ?
  The TR 26.933 was updated to version 1.0.1 and the description of HOA and conclusion/recommendation were for further update.
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  There are 3 contributions of S4-241443, S4-241511, S4-241524 will be discussed, and the goal is to complete the TR.
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
980008 | Study on Diverse audio Capturing system for End-user Devices | FS_DaCED | 9/9/2024 | 70% | SP-221330 | 85% | 90%

## Slide 10: Feasibility Study on Film Grain synthesis (FS_FGS)
Rapporteur: Brian Lee (Dolby Laboratories) - Brian.Lee@dolby.com
Progress since SA4#128
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  The study was on hold, as previously agreed, until more data could be received from JVET
  Video SWG Ad hoc telco agreed to the proposed completion of FS_FGS at SA4#129-e
Any recommendations based on the agreements ?
  Implement the agreement
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Update the Work Item Description (S4-241483)
  Create the TR (S4-241482, S4-241596)
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1000016 | Feasibility Study on Film Grain synthesis | FS_FGS | 3/3/2025 | 30% | SP-230539 | 30% | 

## Slide 11: Feasibility Study on Avatars for Real-Time Communication (FS_AVATAR)
Rapporteur: Bouazizi, Imed, Qualcomm Incorporated, bouazizi AT qti DOT qualcomm DOT com
Progress since SA4#128
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  Input contributions to the Video AHG call were postponed
Any recommendations based on the agreements ?
  No agreements were made during the AHG calls
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Extract and document requirements related to format and security of the avatar representation format
  Document existing formats
  Progress work on avatar integration in 3GPP services like AR calls
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1000019 | Feasibility Study on Avatars for Real-Time Communication | FS_AVATAR | 12/12/2024 | 30% | SP-230544 | 50% | 

## Slide 12: Study on Media enerGy consumption exposuRE and EvaluatioN framework (FS_MediaEnergyGREEN)
Rapporteur: Julien Lemotheux, Orange, julien.lemotheux@orange.com
Progress since SA4#128
One contribution agreed during the MBS Adhoc call (describing Key Issue #2: Monitoring and measurement) and one noted (describing additional use cases defined by SA4).
This has been integrated in new v0.2.1 of TR 26.942 submitted for this meeting.
For the meeting, 9 contributions have been submitted. The goal is to :
  Amend the introduction clause.
  Describe the existing collection and exposure of energy consumption information at NF.
  Complete the clause on use cases with additional use cases defined by SA4.
  Complete the description of the key issues adding a description of KI#3 Evaluation framework.
  Initiate the work the potential solution to Key issue #1 (Information exposure).
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1030004 | Study on Media enerGy consumption exposuRE and EvaluatioN framework | FS_MediaEnergyGREEN | 3/3/2025 | - | SP-240481 | 15% | 

## Slide 13: Study on Media Messaging (FS_MeMe)
Rapporteur: Thomas Stockhammer, Qualcomm Incorporated, tsto@qti.qualcomm.com
Progress since SA4#128
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  No contributions in the Adhoc calls
  Progress externally in IETF MIMI and MPEG
Any recommendations based on the agreements ?
  None
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Inputs on IETF MIMI and 3GPP Messaging, Spatial Video Messaging Format, Media Messaging Format
  The work plan in S4-241474 proposes an extended MBS SWG AHG online session for 3 days in mid of October  agree this
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1030005 | Study on Media Messaging | FS_MeMe | 12/12/2024 -> 3/3/2025 | - | SP-240477 | 10% | 

## Slide 14: Study on Advanced Media Delivery (FS_AMD)
Rapporteur:
Thomas Stockhammer, Qualcomm Incorporated, tsto@qti.qualcomm.com
Progress since SA4#128
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  Good progress on the following topics: Specification Structure (5->10%), Common Client Metadata (5->60%), Multi-CDN and Multi-Access Media Delivery (20->25%), DRM and conditional access (5->20%), In-session Unicast Repair for Object Distribution (10->20%), MBS User Service and Delivery Protocols for eMBMS (5->10%), Selected MBMS Functionalities not supported in MBS (5->10%), Improved QoS Support (20->30%)
  All endorsed CRs are referenced in the work plan for this meeting in clause 3 in S4-241465 and online here
Any recommendations based on the agreements ?
  Take the work endorsed in the AHG telcos as basis for future work and accept that the progress has raised to 19%
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  24 Input contributions received for all 13 topics included in the study. In some cases, we have multiple inputs and we need to discuss how to merge the inputs
  Two new key issues have been received: New KI Multi AS dynamic content generation and a sample solution, SCONE-PRO and 5G Media Streaming
  The work plan in S4-241465 proposes an extended MBS SWG AHG online session for 3 days in mid of October  agree this
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1030006 | Study on Advanced Media Delivery | FS_AMD | 12/12/2024 | - | SP-241011 | 15% | Revised SID

## Slide 15: Study of 5G Real-time Transport Protocol Configurations, Phase 2 (FS_5G_RTP_Ph2)
Rapporteur:
Igor Curcio, Nokia Corporation, igor.curcio@nokia.com
Bo Burman, Ericsson, bo.burman@ericsson.com : TR editor.
Progress since SA4#128
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  No documents were agreed
  5 documents were endorsed (AL-FEC awareness, RTCP messages and header extension for XR services, dynamic traffic characteristics of RTP senders (and related header extension))
Any recommendations based on the agreements ?
  There were no agreements. It is the opinion of the rapporteur that the endorsed status should not be used.
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Discuss contributions in the areas of MID packet filtering, PDU sets (size, multiple media types, RTP retransmission, data burst marking, AL-FEC, lonely PDUs), AL-FEC, support of XR services, RTP multiplexing and multiple sessions, dynamic traffic characteristics of RTP senders.
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1030007 | Study of 5G Real-time Transport Protocol Configurations, Phase 2 | FS_5G_RTP_Ph2 | 12/12/2024 | - | SP-240482 | 40% | 

## Slide 16: Study on Beyond 2D Video (FS_Beyond2D)
Rapporteur:
Jiayi Xu, xujiayi@chinamobile.com
Progress since SA4#128
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
6 contribution was agreed upon during the Video Adhoc call, and 7 contributions were discussed on the following topics:
  Agreed to work on the representation formats and a template to collect and document information on representation formats (for TR).
  Agreed a summary of AR video capabilities from TS 26.119 (for TR).
  Agreed the evaluation methodology for multi-view content (for PD).
  Agreed a B2D scenario on UE-to-UE Live Streaming (for PD).
  Reviewed quality example and codec characteristic of the point cloud representation format.
  Discussed the content, tools, and candidate sequences for multi-view, sterescopic 3D video, and point cloud representation format.
Any recommendations based on the agreements ?
None
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
Discuss 5 proposed representation formats (S4-241481 & 1488 & 1518 & 1519 & 1620)
Discuss the quality evalution methodologies (S4-241494 & 1520)
Others (Scenarios: S4-241618 TR: 1491 PD: 1492 TP:1493)
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1030008 | Study on Beyond 2D Video | FS_Beyond2D | 3/3/2025 | 10% | SP-240479 | 12% | 

## Slide 17: Study on Audio Codec APIs (FS_ACAPI)
Rapporteur:
Stefan Döhla (stefan DOT doehla AT iis DOT fraunhofer DOT de)
Progress since SA4#128
No ad-hoc calls between SA4#128 and SA4#129-e
One contribution (S4-241479) on registration of 3GPP’s codecs as WebCodecs
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1030009 | Study on Audio Codec APIs | FS_ACAPI | 3/3/2025 | 10% | SP-240480 | 15% | Small increments

## Slide 18: Study on Haptics in 5G Media Services (FS_HapticsMed)
Rapporteur:
Gaëlle Martin-Cocher, InterDigital (Gaelle.Martin-Cocher@InterDigital.com)
Progress since SA4#128
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
Any recommendations based on the agreements ?
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Agree TR skeleton, Time Plan and revised SID.
  Review and agree use cases as baseline (5 contributions), possibly merge some similar contributions
  Review and agree contribution on haptics formats and device types
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1030002 | Study on Haptics in 5G Media Services | FS_HapticsMed | 3/3/2025 | - | SP-240979 | 0% | 
FS_HapticsMed

## Slide 19: Study on Spatial Computing for AR Services (FS_ARSpatial)
Rapporteur:
Hamza, Ahmed, InterDigital Canada, <Ahmed.Hamza@InterDigital.com>
Progress since SA4#128
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  None
Any recommendations based on the agreements ?
  None
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  SA4#129-e is the first meeting discussing input contributions on this new study
  Review 3 input contributions (S4-241605, S4-241607, and S4-241608)
  Agree Time Plan and initial TR skeleton
  Review and agree documentation of core spatial computing functions
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1040022 | Study on Spatial Computing for AR Services | FS_ARSpatial | 6/6/2025 | - | SP-240927 | 0% |