3GPP TSG SA WG4#129-e                                                                      	TDoc S4-241690

Online, 19th – 23rd Aug, 2024                                          	Revision of S4-241496

Source:	Huawei Technologies Co., Ltd. (Rapporteur)

Title:	Timeplan for IVAS_Codec_Ph2 Work Item v0.1.0

Version:	0.1.0

Agenda Item:	7.5

Document for:	Discussion and Agreement

# Introduction

The IVAS_Codec_Ph2 work item has been approved at the SA plenary #104 in document SP-241000. The work item has the following objectives:

- A fixed-point C-code to be part of TS 26.251 having:

  - Same functionalities and equivalent performance as the floating-point C-code in TS 26.258.

  - Full interoperability with floating-point C-code in TS 26.258.

  - Comparable complexity as the floating-point C-code in TS 26.258.

This includes verification of 3rd party delivered code and necessary adaptation to the latest version of TS 	26.258. This might include some alignment of floating-point C-code in TS 26.258.

- Characterization of the IVAS codec based on the floating-point and fixed-point C-codes, and documentation of characterization results into TR 26.997.

- Enhancements to codec conformance test procedures and criteria.

- Definition of relevant tiers of functionality to be implementable on a wide range of UEs with different capabilities, balancing user experience and implementation complexity/cost.

- Enhancements to the RTP payload format and SDP negotiation, including split rendering operation.

- Update relevant system and service specifications.

# Timeplan

The timeplan for the execution of the IVAS_Codec_Ph2 work item objectives is proposed in the following table.

| Meeting | Objectives |
| --- | --- |
| TSG SA#104 (18th – 21st June 2024) | - IVAS_Codec_Ph2 Work Item approved by SA Plenary |
| SA4#129-e (16th – 23rd August 2024, online) | - Agree on initial time plan |
| 31st August 2024 | - Delivery of IVAS fixed-point Decoder and Renderer by Ittiam to SA4, fulfilling the FL-to-FX requirements |
| Audio SWG call, TBD | - Review progress of the fixed-point code conversion |
| 30th September 2024 | - Delivery of IVAS fixed-point Encoder by Ittiam to SA4, fulfilling the FL-to-FX requirements, covering the following operation modes: - Mono (EVS) - ISM (core coder) - Stereo - MCT |
| Audio SWG call, TBD | - Review progress of the fixed-point code conversion |
| 31st October 2024 | - Delivery of IVAS fixed-point Encoder by Ittiam to SA4, fulfilling the FL-to-FX requirements, covering the following operation modes: - MASA - SBA - Parametric modes |
| Audio SWG call, TBD | - Review progress of the fixed-point code conversion |
| SA4#130 (18th – 22nd November 2024) | - Verification and Agreement by SA4 on Delivery by Ittiam of IVAS fixed-point Decoder and Renderer, fulfilling the FL-to-FX requirements |
| 30th November 2024 | - Delivery of complete IVAS fixed-point Encoder by Ittiam to SA4, fulfilling the FL-to-FX requirements, including the following operation modes: - Combined formats |
| Audio SWG call, TBD | - Review progress of the fixed-point code conversion |
| TSG SA#106 (10th – 12th December 2024) | - Approval by TSG SA (SA#106) of Delivery of IVAS fixed-point Decoder and Renderer, fulfilling the FL-to-FX requirements, based on agreement in SA4 |
| SA4#131 (17th – 21st February 2025) | - Verification and Agreement by SA4 on Delivery by Ittiam of IVAS fixed-point Encoder, fulfilling the FL-to-FX requirements - Finalization of IVAS characterization permanent documents, including: - IVAS-7b Processing Plan for Characterization Phase - IVAS-8b Test Plan for Characterization Phase |
| TSG SA#107 (12th – 14th March 2025) | - Approval by TSG SA (SA#107) of Delivery of IVAS fixed-point Encoder, fulfilling the FL-to-FX requirements, based on agreement in SA4 |
| SA4#131-bis-e (7th – 11th April 2025) | - Verification of IVAS fixed-point C-code for TS 26.251 having - Same functionalities and equivalent performance as the floating-point C-code in TS 26.258. - Full interoperability with floating-point C-code in TS 26.258. - Comparable complexity as the floating-point C-code in TS 26.258. Note: This includes necessary adaptation to the latest version of TS 26.258 on top of the delivery by Ittiam and might include some adaptation of the floating-point C-code in TS 26.258. - Decision on launching characterization tests |
| April – May 2025 | - IVAS characterization testing |
| SA4#132 (19th – 23rd May 2025) | - Characterization test results available for analysis - Agreement on TS 26.251 (IVAS fixed-point C-code) - Agreement on characterization test results to be incorporated into TR 26.997 - Agreement on relevant CRs for: - Enhanced conformance procedures and criteria - Definition of relevant tiers of functionality to be implementable on a wide range of UEs with different capabilities, balancing user experience and implementation complexity/cost - Enhancements to the RTP payload format and SDP negotiation, including split rendering operation - Agreement on CRs for update of relevant system and service specifications |
| TSG SA#108 (10th – 13th June 2025) | - TS 26.251 (IVAS fixed-point C-code), for approval - CR to TR 26.997 on IVAS Codec characterization, for approval - CR to TS 26.114 on enhanced support for the IVAS Codec, for approval - CR to TS 26.117 with reference to TS 26.251, for approval - CR to TS 26.119 on enhanced support for the IVAS Codec, for approval - CR to TS 26.250 with definition of relevant tiers for implementation of IVAS, for approval - CR to TS 26.252 on enhanced conformance procedures and criteria, for approval - CR to TS 26.253 on enhanced RTP Payload Format and SDP negotiation, including split rendering operation - Potential CR to TS 26.258 on alignment between floating-point code and fixed-point code in TS 26.251, for approval |