## Slide 1: Release-18/19 Time Plan Proposal SA5#151, 9 – 13 October, 2023
Zou Lan, 3GPP SA5 Chair, HUAWEI
Thomas Tovinger, 3GPP SA5 Vice-Chair, ERICSSON
Anatoly Andrianov, 3GPP SA5 Vice-Chair, NOKIA
Gerald Görmer, SA5 CH SWG Chair, MATRIXX Software

## Slide 2: Background
Rel-18 and Rel-19 release schedule was discussed in SA#101. SA5 needs to align the SA5 work plan with the overall 3GPP release schedule.
This tdoc uses the following references:
  SA#101 3GPP Work Plan review at Plenary #101 (SP-231204)

## Slide 3: Background information from latest 3GPP Work Plan review at Plenary #101
Ref: SP-231204
Rel-18 Highlights:
<Stage2 normative> is frozen in Jun.2023.
<Stage 3(CT&SA)> and <RAN completion> are planned to be frozen in Mar.2024.
Rel-19 Highlights:
<Stage 2 normative is planned to be frozen in Dec.2024.
<Stage 3(CT&SA)> and <RAN completion> are planned to be frozen in Sep.2025.

## Slide 4: Background information from latest 3GPP Work Plan review at Plenary #101- Release 18
Ref: SP-231204

## Slide 5
Release 18 timeline– figure with SA5 (For integrated to SA timeline)
#93-e
SA1 Stage 1 100%
RAN4_Perf
Stage 3 (CT & SA)
RAN1
Stage 2 (SA2, SA6,…) Normative
RAN4
content def.
Release 18
Note: All starting dates are indicative
#94-e
#95-e
#96
#97-e
#98-e
#99
#100
#101
#102
#103
#104
#105
RAN Content def.
2022
2023
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Sep.
Dec.
Dec.
Dec.
Maint.
Maint.
ASN.1 & Open APIs
ASN.1
1st review
TSGs
2021
RAN Completion (RAN2/3/4core)
Stage 1 /Stage2/Stage 3 (SA5) Normative
2024
Now
stage1
stage2
stage3

## Slide 6
Release 18 Freezes and other milestones, sorted by dates :
  Sept 2021 (TSG#93): Stage 1: 80% normative work; SA Workshop; joint SA/RAN/CT meeting
  Dec 2021 (TSG#94):
    Stage 1: 100% normative work
    RAN/SA/CT joint meeting on Rel-18 content; SA2 Work Items prioritization; RAN Content Definition
  Mar 2022 (TSG#95): RAN4-lead WIDs specified
  June 2022 (#96) till March 2023 (#99): no specific deadline
  June 2023 (TSG#100): Stage 2 Functional work (SA2 and SA6) Freeze
  Sep 2023 (TSG#101):
    RAN1 freeze (before maintenance)
    Freeze for SA3 (stages 2 & 3) – maintenance to continue
  Dec 2023 (TSG#102):
    RAN1 freeze (after maintenance)
    RAN2, RAN3, RAN4Core freeze (before maintenance)
  Mar 2024 (TSG#103):
    RAN2, RAN3, RAN4Core freeze maintenance
    Stage 3 (all CT WGs; SA WGs involved with Stage 3) freeze
    (also first review of ASN.1)
  June 2024 (TSG#104):
    RAN4Perf freeze
    “coding freeze”. Freeze of:ASN-1; Open APIs
Release 18 timelines – with SA5 text
SA5 OAM Release 18 Freezes and other milestones, sorted by dates :
  Mar 2022 (TSG#95): SA5 SIDs/WIDs specified
  Mar 2023 (TSG#99) and Jun 2023(TSG#100): SA5 SID concluded and Rel-18 WID started if needed
  Sep 2023 (TSG#101): Stage 1 work freeze
  Dec 2023 (TSG#102): Stage 2 Functional work Freeze and stage 3(OAM/CN related), provide inputs to CT
  Mar 2024 (TSG#103): Stage 2 Functional work Freeze and stage 3 (RAN related)
Support of SA2, provide inputs to CT
Support of RAN
Now
Now
SA5 CH Release 18 Freezes, sorted by dates :
  Dec 2023 (TSG#102): Stage 2 Functional work Freeze
  Mar 2024 (TSG#103): Stage 3 Functional work Freeze
  June 2024 (TSG#104): Stage 3 Code freeze for ASN.1 and OpenAPI yaml code

## Slide 7: Background information from endorsed Rel-19 planning workshop at Plenary #98e
Ref: SP-221353

## Slide 8: Background information from latest 3GPP Work Plan review at Plenary #101 – Release 19
Ref: SP-231204

## Slide 9
Release 19 timeline– figure with SA5
SA5 will continue Rel-19 topic discussion based on the collected information in SA5#149e
Rel-19 planning
SA Rel-19 workshop
SA stage2
1st package
SA stage2
final package
SA5 OAM Rel-19 preparation

## Slide 10
Release 19 timeline
#101
#102
#103
#104
#105
#106
#107
#108
#109
#110
#111
#112
#99
RAN4
content def.
RAN Content def.
2024
2025
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Mar.
Dec.
Dec.
Dec.
2026
RAN4_Perf
Stage 3 (CT & SA including SA5 OAM)
RAN1
Stage 2 (SA2, SA5 OAM,SA6,…) Normative
RAN Completion (RAN2/3/4core), SA5 OAM
ASN.1 & Open APIs
St.2 Content approval
#100
Jun.
2023
Now
100%
SA1/SA5 Stage 1 80%
TSGs
RAN Rel-19 workshop
SA Rel-19
Workshop
Extended stage2 (SA5 OAM)
SA5 CH Study Stage 2 & 3 (SA5 CH ) Normative
Extended stage1 (SA5 OAM)
Release 19 timeline– figure with SA5 (For integrated to SA timeline)

## Slide 11
Release 19 timeline– figure with SA5 OAM (considering of sync with SA1/SA2/SA6/RAN/CT) (for SA5 internal use)
Categorization of SA5 OAM work area:
Standalone OAM
SA1 related OAM
SA2/6 related OAM
RAN/CT related OAM
Key sync periods and potential sync consideration:
① Jun.2023 (SA5#150) ~Dec.2023 (SA5#152/ TSG#102) coordination with SA1 on management requirements using DP
② Oct.2023 (SA5#151) ~Dec.2023 (SA5#152/TSG#102): First Rel-19 Sis/WIs discussion time window. First package of Sis/WIs are targeted to be ready in TSG#102.
③ Jan.2024 (SA5#153) ~Sep,2025 (TSG#109): Rel-19 work time window.
SA2/SA6/CT related stage2 should be ready in TSG#106, to be able to sync with SA2/SA6/CT discussion.
Standalone OAM/RAN related stage2 should be ready in TSG#108, to be able to sync with RAN discussion.
④ Jun (SA5#155)~Sep. 2024 (SA5#156/TSG#105): Placeholder time window for new WI/SI (only if there are TU left).
⑤ Jun (SA5#150) ~Dec.2023 (SA5#152/ TSG#102) potential sync time window with SA1(6 months).
⑥ Apr (SA5#154)~Dec,2024 (SA5#158): potential sync time window with SA2/SA6(9 months).
⑦Oct,2024(SA5#157)~Sep,2025 (TSG#109): potential sync time window with RAN/CT (12 months).
#101
Note: All starting dates are indicative
#102
#103
#104
#105
#106
#107
#108
#109
#110
#111
#112
#99
RAN4
content def.
RAN Content def.
2024
2025
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Mar.
Dec.
Dec.
Dec.
2026
RAN4_Perf
Stage 3 (CT & SA)
RAN1
Stage 2 (SA2, SA6,…) Normative
RAN Completion (RAN2/3/4core)
ASN.1 & Open APIs
St.2 Content approval
#100
Jun.
2023
Now
100%
SA1 Stage 1 80%
TSGs
RAN Rel-19 workshop
SA Rel-19
Workshop
SA5 Stage 2 and stage 3 work (RAN related OAM)
SA5 OAM Rel-19 Timeline
SA5#151~152:New Rel-19 SIDs/WIDs
SA5#155~156:Potential place holder (if there are spare TU)
SA5 Stage 2 (SA2/6 related OAM) and CT related stage3
②
Work item 15 months
Studies 6 months
①
④
Studies (SA5 standalone OAM)
③
⑥ 9 months SA2/6 sync
⑦ 12 months RAN/CT sync
⑤ 6 months SA1 sync
normative (SA5 standalone OAM)
SA5#150~152:Follow SA1 discussion with DP

## Slide 12
Release 19 timelines – with SA5 text
SA5 OAM Release 19 Freezes and other milestones, sorted by dates :
Oct.2023 (SA5#151) ~Dec.2023 (SA5#152/TSG#102): First Rel-19 Sis/WIs discussion time window. First package of Sis/WIs are targeted to be ready in TSG#102.
Jan.2024 (SA5#153) ~Sep,2025 (TSG#109): Rel-19 work time window.
  SA2/SA6/CT related stage2 should be ready in TSG#106, to be able to sync with SA2/SA6/CT discussion.
  Standalone OAM/RAN related stage2 should be ready in TSG#108, to be able to sync with RAN discussion.
Jun (SA5#155)~Sep. 2024 (SA5#156/TSG#105): Second Rel-19 WIs discussion time window (only if there are TU left). Second package of Sis/WIs are targeted to be ready in TSG#105 .
Support of SA2, provide inputs to CT
Support of RAN
Release 19 Freezes and other milestones, sorted by dates :
  June 2023: RAN workshop on Rel-19 content, SA workshop on Rel-19 content
  Sept 2023 (TSG#101):
    Stage 1: 80% normative work
    Approve 1st part of SA Stage 2 package (SA/CT)
  Dec 2023 (TSG#102):
    Stage 1: 100% normative work
    RAN1/2/3 Content Definition
    Approve final package of SA Stage 2 with RAN/CT
  Mar 2024 (TSG#103): RAN4 Content Definition
  Dec 2024 (TSG#106): Stage 2 Functional work (SA2 and SA6) Freeze (working assumption)
  June 2025 (TSG#108): RAN1 freeze
  Sept 2025 (TSG#109):
    RAN2, RAN3, RAN4Core freeze
    Stage 3 (all CT WGs; SA WGs involved with Stage 3) freeze (working assumption)
  Dec 2025 (TSG#110):
    RAN4Perf freeze
    “coding freeze”. Freeze of:ASN-1; Open APIs (working assumption)
Now
SA5 CH Release 19 Freezes and other milestones, sorted by dates :
May 2024 (SA5#155): First Rel-19 SIs/WIs discussion time window based on SA2 SID.
Aug 2024 (SA5#156): Rel-19 SIs/WIs check point with SA2 SIs approvals.
Nov 2024 (SA5#158): Target for SID completion and First Rel-19 WIs discussion time window based on SA2 WIs
Jan 2025 (SA5#159): Rel-19 WIs package update
Dec 2025 (SA#110): Rel-19 WIs package complete

## Slide 13: Leaders’ recommendation for SA5 OAM time planning
SA5 OAM Release 18 planning：
Mar 2022 (TSG#95): SA5 SIDs/WIDs specified
Mar 2023 (TSG#99) and Jun 2023(TSG#100): SA5 SID concluded and Rel-18 WID started if needed
Sep 2023 (TSG#101): Stage 1 work freeze
Dec 2023 (TSG#102): Stage 2 Functional work Freeze and stage 3(OAM/CN related), provide inputs to SA2 and CT
Mar 2024 (TSG#103): Stage 2 Functional work Freeze and stage 3 (RAN related)
SA5 OAM Release 19 planning workshop：
June 2023 SA Rel-19 workshop: Provide SA5 relevant Rel-19 inputs/planning to Jun SA workshop
Sep 2023 (TSG#101): Submit Rel-19 1st package following 3GPP timelines
Dec 2023 (TSG#102): Submit Rel-19 final package following 3GPP timelines
SA5 OAM Release 19 planning:
Oct.2023 (SA5#151) ~Dec.2023 (SA5#152/TSG#102): First Rel-19 Sis/WIs discussion time window. First package of Sis/WIs are targeted to be ready in TSG#102.
Jan.2024 (SA5#153) ~Sep,2025 (TSG#109): Rel-19 work time window.
  SA2/SA6/CT related stage2 should be ready in TSG#106, to be able to sync with SA2/SA6/CT discussion.
  Standalone OAM/RAN related stage2 should be ready in TSG#108, to be able to sync with RAN discussion.
Jun (SA5#155)~Sep. 2024 (SA5#156/TSG#105): Second Rel-19 WIs discussion time window (only if there are TU left). Second package of Sis/WIs are targeted to be ready in TSG#105 .
Note:
We should strictly follow the 3GPP release timelines (especially to align the stage 3 freeze date).
For the CT related features, we need to provide inputs to CT as early as possible.
Management aspects which have no CN/RAN dependency or which needs to influence CN/RAN should be addressed as early as possible.
Avoid exception requests as much as possible, and in case the work could not be completed according to the time plan, either narrow down the scope of the work, or postpone the work to next release.
Now
Now
Now

## Slide 14: Leaders’ recommendation for SA5 CH time planning
SA5 CH Release 18 progressing：
Dec 2023 (TSG#102): Stage 2 Functional work Freeze
Mar 2024 (TSG#103): Stage 3 Functional work Freeze
June 2024 (TSG#104): Stage 3 Code freeze for ASN.1 and OpenAPI yaml
SA5 CH Release 19 planning:
May 2024 (SA5#151): First Rel-19 SIs/WIs discussion time window based on SA2 SID.
Aug 2024 (SA5#156): Rel-19 SIs/WIs check point with SA2 SIs approvals.
Nov 2024 (SA5#158): Target for SID completion and First Rel-19 WIs discussion time window based on SA2 WIs
Jan 2025 (SA5#159): Rel-19 WIs package update
Dec 2025 (SA#110): Rel-19 WIs package complete
Note:
SA5 CH work is related to SA2 Sis/WIs work completion and should not start beforehand

## Slide 15: Detailed view of SA5 OAM relation with other groups (for SA5 internal use)
SA1
Requirements
SA2
Architecture
SA3
Security
SA4
Media
SA5 OAM
Stage 3
SA6
Apps/MC
RAN
Radio Access
CT – Protocols & Coding
Stage 1
Stage 2
Stage 3
time
SA5 OAM
Stage 1
SA5 OAM
Stage 2
3GPP Internal Cooperation:
  1. SA1: Management related requirements
  2. SA2: Cooperation on EE, AIML, NWDAF, CN NF management
  3. SA3: OAM Security
  4. SA4: QoE data collection
  5. SA6: MEC, Exposure
  6. CT: Trace, OpenAPI stage3 coordination
  7. RAN1: AIML,EE
  8. RAN3: SON, EE, data collection, AIML, RAN NF management
3GPP External Cooperation:
  1. GSMA: OPG SBI-OAM, Open Gateway, GST requirements (NG.116) as input
  2. CAMARA: support of dev-friendly APIs delivering Open Gateway services (i.e., service APIs)
  3. ETSI ZSM: management architecture, intent, closed loop control
  4. ETSI EE/ITU-T SG2/SG5/SG13: EE
  5. TMF: Autonomous networks level and evaluation, intent, support of TM Forum APIs delivering Open Gateway OAM (i.e., operate APIs)
  6. ONAP: reuses SA5 MnS
  7. O-RAN: reuse SA5 MnS
GSMA/
CAMARA/ETSI ZSM/
ETSI EE/
ITU-T SG2/SG5/SG13/
TMF/
ONAP/
O-RAN

## Slide 16: Change History
SA5 #141e | S5-221173 SA5 Rel-18 time plan proposal for OAM
SA5 #146 | S5-226377(endorsed) Rel-18&Rel-19 Time Plan Proposal for OAM
SA5#146bis-e | S5-231032(endorsed) Rel-18&Rel-19 Time Plan Proposal for OAM
SA5#147 | S5-232446 Rel-18&Rel-19 Time Plan Proposal for OAM Editorial update and add provide inputs to SA2 in slide 9
SA5#147 | S5-232763(endorsed) Rel-18&Rel-19 Time Plan Proposal for OAM Update slide 8
SA5#148e | S5-233263 Rel-18&Rel-19 Time Plan Proposal for OAM Updated according to SA#99, SA5 Rel-19 time plan is added
SA5#149 | S5-234062 Rel-18&Rel-19 time plan proposal for OAM
SA5#150 | S5-235580 Rel-18&Rel-19 time plan proposal for OAM
SA5#151 | S5-236570 Rel-18&Rel-19 time plan proposal

## Slide 17: Thank you!

## Slide 18: Consideration on SA5 OAM R18&R19 time planning(1/2)
General considerations as agreed in S5-221173:
1. We should strictly follow the 3GPP release timelines (especially to align the stage 3 freeze date).
2. For the CT related features, we need to provide inputs to CT as early as possible.
3. Management aspects which have no CN/RAN dependency or which needs to influence CN/RAN should be addressed as early as possible.
4. Avoid exception requests as much as possible, in case the work could not be completed according to the time plan, either narrow down the scope of the work, or postpone the work to next release.
Concrete time planning consideration:
Rel-18 studies:
  For the topics which target to start corresponding work items in Rel-18, the studies need to be closed and corresponding work items be initiated no later than Jun, 2023. This is to leave enough time to produce high quality standardization specification within Rel-18 timeframe. For the leftover work which could not be finalized in the study, it could be considered for potential Rel-19 work.
  It’s also allowed to use the full Rel-18 time for the approved study items if there is no plan for standardization in Rel-18.
Rel-18 work items: all the work items are to be finished strictly following the 3GPP overall time schedule. Rapporteurs are requested to consider reasonable Rel-18 scope and coordinate the work with best utilizing the time.
Rel-19 studies/work items: closely following the SA Rel-19 discussion and provide SA5 relevant inputs if they are available.

## Slide 19
Release 18 timeline– figure with SA5 OAM(for SA5 internal use)
#93-e
SA1 Stage 1 100%
RAN4_Perf
Stage 3 (CT & SA)
RAN1
Stage 2 (SA2, SA6,…) Normative
RAN4
content def.
Release 18
Note: All starting dates are indicative
#94-e
#95-e
#96
#97-e
#98-e
#99
#100
#101
#102
#103
#104
#105
RAN Content def.
2022
2023
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Sep.
Dec.
Dec.
Dec.
Maint.
Maint.
ASN.1 & Open APIs
ASN.1
1st review
TSGs
2021
RAN Completion (RAN2/3/4core)
Stage 1 (SA5 OAM) Normative
Stage 2 Functional and stage 3 work (OAM/CN related),
provide inputs to CT
Stage 2 Functional and stage 3 work (RAN related)
SA5 OAM Rel-18 Timeline
2024
Now