## Slide 1: AI/ML Management – Phase 2: Work plan & guidelines
NEC, Intel
3GPP TSG-SA5 Meeting #159 S5-250800
Sophia-Antipolis, France, 17 – 21 February 2025

## Slide 2: Content
Rel-19 WID objectives
Completion target & allocated TUs
Work plan & key milestones
General guidelines

## Slide 3: AI/ML management – phase 2 (1/3)
Rel-19 WID approved at SA#106 in SP-241944
Objectives:
The objectives of AI/ML management phase 2 work item are to specify the management capabilities to support AI/ML functions defined by 3GPP, including:
  - NG-RAN AIML-based Coverage and Capacity Optimization, and NG-RAN AIML-based Network Slicing defined by RAN3,
  - Model delivery/transfer as defined by RAN1/2,
  - ML model training and AI/ML inference functions for 5GC as defined by SA2, and
  - MDA (Management Data Analytics) as defined by SA5.

## Slide 4: AI/ML management – phase 2 (2/3)
To achieve these objectives, the following work tasks are defined:
WT-1: Specify the AI/ML management capabilities including use cases, requirements and solutions for the relevant AI/ML lifecycle operational steps based on TR 28.858, including:
WT-1.1: Management capabilities for ML model training:
- ML-Knowledge-based Transfer Learning, - ML pre-training and fine-tuning, - ML model training for multiple contexts, - ML training data statistics, - ML model confidence, - Management of Reinforcement Learning, - Sustainable AI/ML for ML training, - ML model Distributed training, - Management of Federated Learning, - ML authentication, - AI/ML prediction latency, - ML explainability.

## Slide 5: AI/ML management – phase 2 (3/3)
WT-1.2: Management capabilities for AI/ML inference emulation:
  - ML inference emulation, - ML inference emulation environment selection.
WT-1.3: Management capabilities for ML model deployment:
  - Enhancements to ML model loading,
  - ML model transfer/delivery.
WT-1.4: Management capabilities for AI/ML inference:
  - Coordination between the ML capabilities, - Sustainable AI/ML for AIML inference, - ML remedial action management, - Managing ML models in use in a live network, - AI/ML prediction latency, - ML explainability.
NOTE: Solutions for the defined use cases shall leverage the already existing specified capabilities in TS 28.105 where applicable.

## Slide 6: Completion target & allocated TUs
Completion target: SA#109, September 2025
Total of 5 SA5 meetings to completion target,
  SA5#159, February 2025
  SA5#160, April 2025
  SA5#161, May 2025
  SA5#162, August 2025
  SA5#163, October 2025
Estimated total time allocation: 5 Tus, an average of ~ 1 TU per meeting
Work Task ID | TU Estimate
1.1 | 1.7
1.2 | 0.4
1.3 | 0.6
1.4 | 1.2

## Slide 7: Plan of work - SA5#159 (February 2025)
Focus is on WT-1.1 and WT-1.2, addressing both stage 1 and stage 2 specifications:
  WT-1: Specify the AI/ML management capabilities including use cases, requirements and solutions for the relevant AI/ML lifecycle operational steps based on TR 28.858, including:
  WT-1.1: Management capabilities for ML model training:
  - ML-Knowledge-based Transfer Learning, - ML pre-training and fine-tuning, - ML model training for multiple contexts, - ML training data statistics, - ML model confidence, - Management of Reinforcement Learning, - Sustainable AI/ML for ML training, - ML model Distributed training, - Management of Federated Learning, - ML authentication, - AI/ML prediction latency, - ML explainability.
  WT-1.2: Management capabilities for AI/ML inference emulation:
  - ML inference emulation, - ML inference emulation environment selection.

## Slide 8: Plan of work - SA5#160 (April 2025)
Priority focus continues WT-1.1 & WT-1.2.
The following WTs are also in the scope of SA5#160 but will be treated a lower priority:
WT-1.3: Management capabilities for ML model deployment:
  - Enhancements to ML model loading,
  - ML model transfer/delivery.
WT-1.4: Management capabilities for AI/ML inference:
  - Coordination between the ML capabilities, - Sustainable AI/ML for AIML inference, - ML remedial action management, - Managing ML models in use in a live network, - AI/ML prediction latency, - ML explainability.

## Slide 9: Plan of work - SA5#161 (May 2025)
All WTs are within the scope of SA5#161.
  Focus on addressing content (both Stages 1 & 2) for WT-1.3 & WT-1.4.
  Aim to finalize some content for CR submission to SA#108, based on accomplishments for WT-1.1 & WT-1.2 or other content.

## Slide 10: Plan of work - SA5#162 (August 2025)
All WTs are within the scope of SA5#163.
Focus on:
  Finalizing work for WT-1.3 & WT-1.4 (both stages 1 & 2).
  Addressing any issues for other WTs.

## Slide 11: Plan of work - SA5#163 (October 2025)
All WTs are within the scope of SA5#163.
Focus on:
  Cleaning up, fixing errors, and resolving any inconsistencies.
  Final check of Stage 2 for all WTs and ensuring alignment between Stage 2 and Stage 3.
  Finalizing Draft CR and converting it into a CR for submission to SA#109.

## Slide 12: Guidance & Recommendations for Contributions
Contributions are encouraged to include a clear and detailed reason for change or justification for their proposed inputs to the specification. Agreed content in the TR alone does not constitute a strong enough justification and does not necessarily always guarantee inclusion in the normative specification.
It is recommended that contributions align with the overall goals and the corresponding Work Item tasks for consistency and relevance.
Contributors are advised to adhere to the planned scope for each meeting to ensure effective progress, as submissions outside the planned agenda may be deprioritized to maintain focus and efficiency.
Companies are encouraged to address controversial issues through offline discussions before F2F meetings. The rapporteur can assist by facilitating discussions via pre-arranged calls or ad hoc meetings to help resolve such issues.
For use cases with multiple, potentially contradictory or competing solutions, it is recommended to resolve discrepancies in advance to build consensus and avoid delays during decision making stage.

## Slide 13: Work plan & key milestones
To ensure a smooth progression towards the September 2025 completion target and the timely completion of all specification stages, the following work plan and key milestones shall be adopted:
  Address a subset of WI work tasks per meeting, adding other WTs progressively in following sessions to maintain focus and ensure manageable discussions, avoiding overload and making each meeting more productive, while ensuring focused and efficient discussions to drive progress, allowing quick resolution of issues and clear next steps.
  Stabilize stage 1 & stage 2 content by end of August meeting (SA5#162), providing a solid foundation for Stage 3 development, minimizing last-minute rework and avoiding stressful times prior to SA#109 (September 2025).
  Continue enhancement of all contents, complete Stage 3 development/finalization and general cleanup of DraftCR content by end of SA5#163 (October 2025), allowing enough time for thorough review and adjustments to ensure a refined, well-reviewed Stage 3 well in time for September target completion.
  The Draft CR approach, adopt the Draft CR approach for SA5 meetings: SA5#160 (April 2025), SA5#161 (May 2025), SA5#162 (August 2025), and SA5#163 (October 2025), to document changes targeting Rel-19 TS 28.105.
    During this period, the group agreed to temporarily withhold Rel-19 CR submissions for the same specification, except for content deemed mature at SA5#161,
    At the end of SA5#161 (May 2025), the group will assess the Draft CR. If all or part of the content is deemed mature, it will be converted and submitted as CRs to SA#108 (June 2025), while the remaining content will continue in the Draft CR process.